## meeting-log
PAS Team Meeting Log
From 'M0 - General Project Requirements.pdf'
"Teams must meet weekly and must keep a meeting log of attendance. This log should be in the repository. This meeting must be distinct from the client meeting."
Date | Attendees | Summary
2024-10-01 | All | Solidified design plan. Action flow will work as follows: 1) Image is captured by camera module, 2) Image is output from module to raspberry pi where an edge object detection model determines if a unique car is visible in the throughlanes, 3) Once unique car is visible, a frame is sent to AWS model for ALPR and other extraction of car characteristics, 4) This information along with the direction the car is facing while moving is used to determine parking facility throughput which is used to increment a counter in a database, 5) Counter data is used as the prediction for parking availability and will be available to access by users through mobile app. Discussed Design Plan Draft work partitioning. Members were assigned focus areas for the project. Members will fill out Statement of Work, Deliverable Artifacts, and Mockups as it relates to their primary focus area.
2024-10-08 | All | Confirmed design plan with Carsten. Carsten offered to be liason with UF staff if need be to test system in campus parking garage. Additionally, Raspberry Pi can be connected to UF WiFi through eduroam, but UF IT may be able to help to allow it to be permanently connected to UF WiFi. Clarified Design Plan Draft work partitions. Worked on Design Plan
2024-10-15 | All | Met with stakeholder Raven. Clarified expectations for pre-alpha build requirements. Need to implement one feature, or atleast have the backend stuff set up. We should use these meetings as weekly scrum meetings or standups to go over what we've done, what we need to do, and any issues that could prevent us from getting what we need done. Used to gauge progress and participation. Clarified use of GitHub Project to track items and hours.
2024-10-22 | All